## Basic Manual Gantt Chart
Project Name | Blockchain for Anti-Money Laundering
Project Deliverable | Publication
Start Date | 2018-01-17
End Date | 2018-08-20 | (Tentative)
Task Name | Start Date | End Date | Duration | Status | Start Date in Number Form | 43118
Project Kickoff | 2018-01-18 | 2018-01-18 | 1 | Completed
Group Formation | 2018-01-18 | 2018-01-18 | 1 | Completed
Meeting # 1 | 2018-01-18 | 2018-01-18 | 1 | Completed
Topic Selection and Design Plan | 2018-01-18 | 2018-01-31 | 14 | Completed
Meeting # 2 | 2018-01-24 | 2018-01-24 | 1 | Completed
Advisor Selection | 2018-01-24 | 2018-01-24 | 1 | Completed
Advisor Commitment | 2018-01-24 | 2018-01-31 | 8 | Completed
Meeting # 3 | 2018-01-29 | 2018-01-29 | 1 | Completed
Meeting # 4 | 2018-01-30 | 2018-01-30 | 1 | Completed
Initial Design Plan Submission | 2018-01-31 | 2018-01-31 | 1 | Completed
Meeting # 5 | 2018-02-01 | 2018-02-01 | 1 | Completed
Meeting with Advisors # 1 | 2018-02-01 | 2018-02-01 | 1 | Completed
Meeting # 6 | 2018-02-04 | 2018-02-04 | 1 | Completed
Online Café Talk | 2018-02-07 | 2018-02-08 | 2 | Completed
Meeting # 7 | 2018-02-10 | 2018-02-10 | 1 | Completed
Meeting with Advisors # 2 | 2018-02-13 | 2018-02-13 | 1 | Completed
Meeting # 8 | 2018-02-17 | 2018-02-17 | 1 | Completed
Meeting # 9 | 2018-02-25 | 2018-02-25 | 1 | Completed
Meeting with Advisors # 3 | 2018-03-03 | 2018-03-03 | 1 | Completed
Meeting with Advisor #4 (Sudip & Craig in person) | 2018-03-06 | 2018-03-06 | 1 | Completed
Meeting #10 | 2018-03-06 | 2018-03-06 | 1 | Completed
Meeting with Dr. Engels & Advisors #5 | 2018-03-07 | 2018-03-07 | 1 | Completed
Meeting # 11 | 2018-03-11 | 2018-03-11 | 1 | Completed
Meeting # 12 | 2018-03-14 | 2018-03-14 | 1 | Completed
First Paper Draft (A) | 2018-02-01 | 2018-03-14 | 42 | Completed
Online Café Talk (Dan) | 2018-03-20 | 2018-03-20 | 1 | Completed
Online Café Talk (Sudip & Tim) | 2018-03-21 | 2018-03-21 | 1 | Completed
Meeting # 13 | 2018-03-22 | 2018-03-22 | 1 | Completed
Meeting with Advisor (Pablo) # 1 | 2018-03-24 | 2018-03-24 | 1 | Completed
Meeting #14 | 2018-03-31 | 2018-03-31 | 1 | Completed
Meeting with Advisor (Pablo) # 2 | 2018-04-10 | 2018-04-10 | 1 | Completed
Meeting with Advisors # 6 | 2018-04-15 | 2018-04-15 | 1 | Completed
Meeting #15 | 2018-04-30 | 2018-04-30 | 1 | Completed
Meeting # 16 | 2018-05-03 | 2018-05-03 | 1 | Completed
Meeting with Advisor (Pablo) # 3 | 2018-05-09 | 2018-05-09 | 1 | Completed
Meeting with Advisors # 7 | 2018-05-15 | 2018-05-15 | 1 | Completed
Meeting # 17 | 2018-05-17 | 2018-05-17 | 1 | Completed
Meeting # 18 | 2018-05-18 | 2018-05-18 | 1 | Completed
Second Paper Draft (B) | 2018-02-01 | 2018-05-18 | 107 | Completed
Meeting # 19 | 2018-05-27 | 2018-05-27 | 1 | Completed
Meeting with Advisor (Pablo) # 4 | 2018-05-30 | 2018-05-30 | 1 | Completed
Meeting # 20 | 2018-06-07 | 2018-06-07 | 1 | Completed
Meeting with Advisors # 8 | 2018-06-20 | 2018-06-20 | 1 | Completed
Meeting # 21 | 2018-07-01 | 2018-07-01 | 1 | Completed
Meeting with Advisors # 9 | ? | ? | #VALUE! | Not Started
Meeting with Dr. Engels & Advisors #10 | ? | ? | #VALUE! | Not Started
Meeting #22 | ? | ? | #VALUE! | Not Started
Meeting #23 | ? | ? | #VALUE! | Not Started
Third Paper Draft - Complete Draft (B) | 2018-02-01 | 2018-07-11 | 161 | In Progress
Peer Review (B) |  |  |  | Not Started
Final Papers (B) | 2018-02-01 | 2018-08-17 | 198 | Not Started
Poster Presentation (B) |  |  |  | In Progress
Lightning Presentation (B) |  |  |  | In Progress
Final Paper/Publication |  |  |  | Not Started