## Project Plan and Gantt
Project Name | Blockchain For Anti Money Laundering
Project Deliverable | Publication
Start Date | 2018-01-17
End Date | 2085-08-20 | (Don't know the exact date yet)
Overall Progress | ~ 5%
Tasks | Start | End | Days | Status
Meetings
Meeting #1 | 2018-01-18 | 2018-01-18 | 1 | Complete
Meeting #2 | 2018-01-24 | 2018-01-24 | 1 | Complete
Meeting #3 | 2018-01-29 | 2018-01-29 | 1 | Complete
Meeting #4 | 2018-01-30 | 2018-01-30 | 1 | Not started
Meeting #5 |  |  | 1 | Not started
Meeting #6 |  |  | 1 | Not started
Meeting #7 |  |  | 1 | Not started
Meeting #8 |  |  | 1 | Not started
Meeting #9 |  |  | 1 | Not started
Meeting #10 |  |  | 1 | Not started
Meeting #11 |  |  | 1 | Not started
Meeting #12 |  |  | 1 | Not started
Meeting #13 |  |  | 1 | Not started
Meeting #14 |  |  | 1 | Not started
Meeting #15 |  |  | 1 | Not started
Meeting with Advisor #1 | 2018-02-01 |  | 1 | Not started
Meeting with Advisor #2 | 2018-02-15 |  | 1 | Not started
Meeting with Advisor #3 | 2018-03-01 |  | 1 | Not started
Meeting with Advisor #4 | 2018-03-15 |  | 1 | Not started
Meeting with Advisor #5 | 2018-04-01 |  | 1 | Not started
Meeting with Advisor# 6 | 2018-04-15 |  | 1 | Not started
Meeting with Advisor# 7 |  |  | 1 | Not started
Meeting with Advisor# 8 |  |  | 1 | Not started
Meeting with Advisor# 9 |  |  | 1 | Not started
Meeting with Advisor# 10 |  |  | 1 | Not started
Meeting with Advisor# 11 |  |  | 1 | Not started
Meeting with Advisor# 12 |  |  | 1 | Not started
Meeting with Advisor# 13 |  |  | 1 | Not started
Meeting with Advisor# 14 |  |  | 1 | Not started
Meeting with Advisor# 15 |  |  | 1 | Not started
Milestones
Advisor Commitment (A) | 2018-01-18 | 2018-01-31 | 13 | In progress
Initial Problem/Plan (A) | 2018-01-18 | 2018-01-31 | 13 | In progress
First Paper Draft (A) | 2018-01-31 | 2018-03-14 | 42 | Not started
Second Paper Draft | ? | ? | #VALUE! | Not started
Third Paper Draft (B) |  |  |  | Not started
Peer Review (B) |  |  |  | Not started
Final Papers (B) |  |  |  | Not started
Poster Presentation (B) |  |  |  | Not started
Lightning Presentation (B) |  |  |  | Not started
Final Paper/Publication | 2018-01-18 | 2018-08-20 | 214 | In progress