## Basic Manual Gantt Chart
Project Name | Blockchain for Anti-Money Laundering
Project Deliverable | Publication
Start Date | 2018-01-17
End Date | 2018-08-20 | (Tentative)
Task Name | Start Date | End Date | Duration | Status | Start Date in Number Form | 43118
Project Kickoff | 2018-01-18 | 2018-01-18 | 1 | Completed
Group Formation | 2018-01-18 | 2018-01-18 | 1 | Completed
Meeting # 1 | 2018-01-18 | 2018-01-18 | 1 | Completed
Topic Selection and Design Plan | 2018-01-18 | 2018-01-31 | 14 | Completed
Meeting # 2 | 2018-01-24 | 2018-01-24 | 1 | Completed
Advisor Selection | 2018-01-24 | 2018-01-24 | 1 | Completed
Advisor Commitment | 2018-01-24 | 2018-01-31 | 8 | Completed
Meeting # 3 | 2018-01-29 | 2018-01-29 | 1 | Completed
Meeting # 4 | 2018-01-30 | 2018-01-30 | 1 | Completed
Initial Design Plan Submission | 2018-01-31 | 2018-01-31 | 1 | Completed
Meeting # 5 | 2018-02-01 | 2018-02-01 | 1 | Completed
Meeting with Advisor # 1 | 2018-02-01 | 2018-02-01 | 1 | Completed
Meeting # 6 | 2018-02-04 | 2018-02-04 | 1 | Completed
Online Café Talk | 2018-02-07 | 2018-02-08 | 2 | Not Started
Meeting # 7 | 2018-02-10 | 2018-02-10 | 1 | Not Started
Meeting with Advisor # 2 | 2018-02-13 | 2018-02-13 | 1 | Not Started
Meeting # 8 | 2018-02-17 | 2018-02-17 | 1 | Not Started
Meeting with Advisor # 3 | 2018-02-20 | 2018-02-20 | 1 | Not Started
Meeting # 9 | 2018-02-24 | 2018-02-24 | 1 | Not Started
Meeting with Advisor # 4 | 2018-02-27 | 2018-02-27 | 1 | Not Started
Meeting # 10 | 2018-03-03 | 2018-03-03 | 1 | Not Started
Meeting with Advisor # 5 | 2018-03-06 | 2018-03-06 | 1 | Not Started
Meeting # 11 | 2018-03-10 | 2018-03-10 | 1 | Not Started
First Paper Draft Review with Advisor | 2018-03-08 | 2018-03-13 | 6 | Not Started
Meeting with Advisor # 6 | 2018-03-13 | 2018-03-13 | 1 | Not Started
Meeting # 12 | 2018-03-17 | 2018-03-17 | 1 | Not Started
First Paper Draft (A) | 2018-02-01 | 2018-03-14 | 42 | Not Started
Meeting with Advisor # 7 | 2018-03-20 | 2018-03-20 | 1 | Not Started
Meeting # 13 | 2018-03-20 | 2018-03-20 | 1 | Not Started
Online Café Talk | 2018-03-21 | 2018-03-22 | 2 | Not Started
Second Paper Draft (B) |  |  |  | Not Started
Third Paper Draft (B) |  |  |  | Not Started
Peer Review (B) |  |  |  | Not Started
Final Papers (B) |  |  |  | Not Started
Poster Presentation (B) |  |  |  | Not Started
Lightning Presentation (B) |  |  |  | Not Started
Final Paper/Publication |  |  |  | Not Started